## EXAMPLE

PROGRESS REPORT

HYPOTHETICAL ENGINEERING CO., INC.

Agreement No. 9099

Work Order #   (If Applicable)

Progress Billing No. 2

Work Completed Through September 30, 1995

I-240 from Carter Blvd. To Smith Rd.

SHELBY COUNTY

Project Nos. I-240-1(144) 14, 79006-1131-44, 79008-1127-44;

I-55-1(67)0, 79004-1121-44, 79005-1128-44

# PHASE I – SURVEYS

| ITEM NO. | ITEM | % OF WORK | % COMPLETE TO DATE | EFFECTIVE % |
| --- | --- | --- | --- | --- |
| 1 | Establish Alignments | 12.1 | 90.0 | 10.9 |
| 2 | Reference Points | 2.8 | 55.0 | 1.5 |
| 3 | Control Traverses | 8.2 | 100.0 | 8.2 |
| 4 | Bench Levels | 5.7 | 100.0 | 5.7 |
| 5 | Roadway & Driveway Profiles | 4.3 | 90.0 | 3.9 |
| 6 | Cross Sections | 10.3 | 100.0 | 10.3 |
| 7 | Locate Property Lines | 6.4 | 70.0 | 4.5 |
| 8 | Topo Surveys | 6.0 | 80.0 | 4.8 |
| 9 | Drainage Surveys | 2.8 | 30.0 | 0.8 |
| 10 | Utility Surveys | 2.8 | 60.0 | 1.7 |
| 11 | R/W & Utility Research | 0.7 | 100.0 | 0.7 |
| 12 | Note Reduction & Other Calculations | 7.4 | 80.0 | 5.9 |
| 13 | Plot Base Maps | 5.7 | 80.0 | 4.6 |
| 14 | Plot Cross Sections | 3.2 | 80.0 | 2.6 |
| 15 | Supervision | 5.7 | 75.0 | 4.3 |
| 16 | Stake R.O.W. | 7.4 | 0 | - |
| 17 | Travel Time | 8.5 | 75.0 | 6.4 |
|  | EFFECTIVE PERCENT OF PHASE I: |  |  |  |
|  | WORK COMPLETED TO DATE |  |  | 76.8 |
|  | LESS WORK COMPLETED TO DATE LAST INVOICE |  |  | 70.8 |
|  | WORK COMPLETED THIS PAY PERIOD* |  |  | 6.0 |

NET FEE CEILING                                            $10,000.00

*WORK COMPLETED THIS PAY PERIOD               x 6.0%

-------------

NET FEE THIS PAY PERIOD                          $     600.00

ALSO SUPPLY A BRIEF NARRATIVE OF YOUR PROGRESS AS WELL

Revised 11/9/1998