## Sheet1
STATUS OF SR112-DAVIDSON COUNTY, PIN: 103764.00, 19046-2214-14
Total Tracts | 99
Appraisals Received (Includes NPPs) | 91
Appraisals Being Reviewed | 4
Remaining Appraisals | 4
Remaining Appraisals- Due Dates | 7/1/17, 7/15/17, 7/28/17 | Plans revisions have delayed some of these.
Tracts Turned In For Closing/Have ROE/Not Closed | 9 | Waiting on lenders/lien releases.
Tracts Turned In For Condemnation/No Possession | 10
Tracts Closed | 1
Tracts Turned In For Condemnation/Have Possession | 0
Tracts Being Negotiated | 71