## EXAMPLE

PROGRESS REPORT

HYPOTHETICAL ENGINEERING CO., INC.

Agreement No. 9099

Work Order #   (If Applicable)

Progress Billing No. 2

Work Completed January 31, 2015 through February 28, 2015

I-240 from Carter Blvd. To Smith Rd.

SHELBY COUNTY

PIN: 100000.00

Project Nos. I-240-1(144) 14, 79006-1131-44, 79008-1127-44;

I-55-1(67)0, 79004-1121-44, 79005-1128-44

# PHASE I – SURVEYS

Work Completed To Date

| ITEM NO. | ITEM | % OF WORK | % COMPLETE TO DATE | EFFECTIVE % |
| --- | --- | --- | --- | --- |
| 1 | Establish & Stake Alignments | 12.1 | 90.0 | 10.9 |
| 2 | Update Survey | 2.8 | 55.0 | 1.5 |
| 3 | Control Traverses | 8.2 | 100.0 | 8.2 |
| 4 | Set Aerial Control | 5.7 | 100.0 | 5.7 |
| 5 | Bench Levels | 4.3 | 90.0 | 3.9 |
| 6 | Develop Digital Terrain Model | 10.3 | 100.0 | 10.3 |
| 7 | R.O.W., Deed & Utility Research | 6.4 | 70.0 | 4.5 |
| 8 | Property Owner Contact | 6.0 | 80.0 | 4.8 |
| 9 | Locate Property & Present R.O.W. Lines | 2.8 | 30.0 | 0.8 |
| 10 | Obtain Topo/Verify Aerial | 2.8 | 60.0 | 1.7 |
| 11 | Drainage Surveys (Culverts) | 0.7 | 100.0 | 0.7 |
| 12 | Bridge Surveys (bridge details, stream alignment, topo, profile, flood plain sections, high water, etc. | 7.4 | 80.0 | 5.9 |
| 13 | Railroad Surveys | 5.7 | 80.0 | 4.6 |
| 14 | Utilities | 3.2 | 80.0 | 2.6 |
| 15 | Stake R.O.W. & Easements | 5.7 | 75.0 | 4.3 |
| 16 | Stake Sounding Holes. | 7.4 | 0 | - |
| 17 | Note Reduction & other Calculations | 8.5 | 75.0 | 6.4 |
| 18 | Plot Plan, Profiles, Property Map, Drainage Map, Bridge Survey, Control Point Table, etc. |  |  |  |
| 19 | Supervision |  |  |  |
| 20 | Travel Time |  |  |  |
|  | EFFECTIVE PERCENT OF PHASE I: |  |  |  |
|  | WORK COMPLETED TO DATE |  |  | 76.8 |
|  | LESS WORK COMPLETED TO DATE LAST INVOICE |  |  | 70.8 |
|  | WORK COMPLETED THIS PAY PERIOD* |  |  | 6.0 |

NET FEE CEILING                                            $10,000.00

*WORK COMPLETED THIS PAY PERIOD               x 6.0%

-------------

NET FEE THIS PAY PERIOD                          $     600.00

ALSO SUPPLY A BRIEF NARRATIVE OF YOUR PROGRESS AS WELL

Revised 7/2/2015