## EXAMPLE

PROGRESS REPORT

HYPOTHETICAL ENGINEERING CO., INC.

Agreement No. 9099

Work Order #   (If Applicable)

Progress Billing No. 2

Work Completed February 28, 2015 through March 31, 2015

I-240 from Carter Blvd. To Smith Rd.

SHELBY COUNTY

PIN 100000.00

Project No. I-240-1(144) 14, 79006-1131-44

# PHASE II – PRELIMINARY PLANS

| ITEM NO. | ITEM | % OF WORK | % COMPLETE TO DATE | EFFECTIVE % |
| --- | --- | --- | --- | --- |
| 1 | Engineering Studies | 6.4 | 90.0 | 5.8 |
| 2 | Trace Present Layout Sheets | 12.0 | 40.0 | 4.8 |
| 3 | Typical Sections | 1.8 | 70.0 | 1.3 |
| 4 | Trace Proposed Layout Sheets | 16.8 | 40.0 | 6.7 |
| 5 | Establish Horizontal Geometry | 11.4 | 85.0 | 9.7 |
| 6 | Set Tentative Profiles | 3.9 | 85.0 | 3.3 |
| 7 | Plot Tentative Cross-Sections | 3.9 | 70.0 | 2.7 |
| 8 | Set Tentative R. O. W. Lines | 2.4 | 20.0 | 0.5 |
| 9 | Preliminary PS&E - Revisions | 8.4 | 0 | - |
| 10 | Earthwork Calculations - Adjustments | 9.6 | 30.0 | 2.9 |
| 11 | Drainage Designs | 6.3 | 35.0 | 2.2 |
| 12 | Culvert Cross Sections | 2.4 | 20.0 | 0.5 |
| 13 | Miscellaneous Drafting | 1.5 | 20.0 | 0.3 |
| 14 | Interchange Design | 3.6 | 85.0 | 3.1 |
| 15 | Access to Properties | 1.2 | 25.0 | 0.3 |
| 16 | Field Reviews and Reports | 1.5 | 60.0 | 0.9 |
| 17 | Administration, Conferences, Reporting | 6.9 | 45.0 | 3.1 |
|  | EFFECTIVE PERCENT OF PHASE II: |  |  |  |
|  | WORK COMPLETED TO DATE |  |  | 48.1 |
|  | LESS WORK COMPLETED TO DATE LAST INVOICE |  |  | 42.1 |
|  | WORK COMPLETED THIS PAY PERIOD* |  |  | 6.0 |

NET FEE CEILING                                            $10,000.00

*WORK COMPLETED THIS PAY PERIOD                x 6.0%

-------------

NET FEE THIS PAY PERIOD                          $       600.00

ALSO SUPPLY A BRIEF NARRATIVE OF YOUR PROGRESS AS WELL

Revised 07/02/2015