## EXAMPLE

PROGRESS REPORT

HYPOTHETICAL ENGINEERING CO., INC.

Agreement No. 9099

Work Order #   (If Applicable)

Progress Billing No. 2

Work Completed March 31, 2015 through April 30, 2015

I-240 from Carter Blvd. To Smith Rd.

SHELBY COUNTY

PIN 100000.00

Project Nos. I-240-1(144) 14, 79006-1131-44, 79008-1127-44;

# PHASE III – RIGHT-OF-WAY

| ITEM NO. | ITEM | % OF WORK | % COMPLETE TO DATE | EFFECTIVE % |
| --- | --- | --- | --- | --- |
| 1 | Address Soils and Geology Needs | 12.1 | 90.0 | 10.9 |
| 2 | Update Plans from Incidental Report | 2.8 | 55.0 | 1.5 |
| 3 | Update Drainage Design | 7.2 | 100.0 | 7.2 |
| 4 | Update Cross Road Geometry | 4.7 | 100.0 | 4.7 |
| 5 | Design Driveways | 4.3 | 90.0 | 3.9 |
| 6 | Design Guardrail System | 9.3 | 100.0 | 9.3 |
| 7 | Design Traffic Control Plan (Tentative) | 6.4 | 70.0 | 4.5 |
| 8 | Design Erosion Control Features | 6.0 | 80.0 | 4.8 |
| 9 | Define Right-of-way | 2.8 | 30.0 | 0.8 |
| 10 | Add Miscellaneous Items | 2.8 | 60.0 | 1.7 |
| 11 | Participate in Field Review | 0.7 | 100.0 | 0.7 |
| 12 | Final Review by Consultant | 7.4 | 80.0 | 5.9 |
| 13 | Prepare Preliminary Item No. List With Quantities | 5.7 | 80.0 | 4.6 |
| 14 | Submit Plans for TDOT Review | 3.2 | 80.0 | 2.6 |
| 15 | Revise Per Comments from TDOT Review | 5.7 | 75.0 | 4.3 |
| 16 | Submit Plans for Right-of-way | 7.4 | 0 | - |
| 17 | Prepare Needed Water Quality Permits Applications | 8.5 | 75.0 | 6.4 |
| 18 | Conduct Miscellaneous Business Activities | 3.0 | 50.0 | 1.5 |
|  | EFFECTIVE PERCENT OF PHASE III: |  |  |  |
|  | WORK COMPLETED TO DATE |  |  | 75.3 |
|  | LESS WORK COMPLETED TO DATE LAST INVOICE |  |  | 70.8 |
|  | WORK COMPLETED THIS PAY PERIOD* |  |  | 4.5 |

NET FEE CEILING                                            $10,000.00

*WORK COMPLETED THIS PAY PERIOD               x 4.5%

-------------

NET FEE THIS PAY PERIOD                          $     450.00

ALSO SUPPLY A BRIEF NARRATIVE OF YOUR PROGRESS AS WELL

Revised  07/02/2015