## EXAMPLE

PROGRESS REPORT

HYPOTHETICAL ENGINEERING CO., INC.

Agreement No. 9099

Work Order #   (If Applicable)

Progress Billing No. 2

Work Completed April 30, 2015 through May 31, 2015

I-240 from Carter Blvd. To Smith Rd.

SHELBY COUNTY

PIN 100000.00

Project Nos. I-240-1(144) 14, 79006-1131-44, 79008-1127-44;

# PHASE IV – CONSTRUCTION

| ITEM NO. | ITEM | % OF WORK | % COMPLETE TO DATE | EFFECTIVE % |
| --- | --- | --- | --- | --- |
| 1 | Create New Title Sheet | 12.1 | 90.0 | 10.9 |
| 2 | Compute and Tabulate Earthwork Quantities | 2.8 | 55.0 | 1.5 |
| 3 | Tabulate Guardrail | 7.2 | 100.0 | 7.2 |
| 4 | Tabulate Drainage | 4.7 | 100.0 | 4.7 |
| 5 | Tabulate Ramps and Driveways | 4.3 | 90.0 | 3.9 |
| 6 | Complete Typical Section Details | 8.3 | 100.0 | 8.3 |
| 7 | Calculate and Tabulate Paving Quantities | 6.4 | 70.0 | 4.5 |
| 8 | Create General Note Sheet | 6.0 | 80.0 | 4.8 |
| 9 | Create Index Sheet | 2.8 | 30.0 | 0.8 |
| 10 | Design Traffic Control Plan | 2.8 | 60.0 | 1.7 |
| 11 | Complete Erosion Control Plan | 0.7 | 100.0 | 0.7 |
| 12 | Construct Estimated Roadway Quantities Block | 7.4 | 80.0 | 5.9 |
| 13 | Participate in Field Review | 5.7 | 80.0 | 4.6 |
| 14 | Submit for Construction Checking | 3.2 | 80.0 | 2.6 |
| 15 | Print Grading Quantity Sheets (6 Sets) | 5.7 | 75.0 | 4.3 |
| 16 | Review of Final Plans by Consultant | 7.4 | 0 | - |
| 17 | Submit Final Plans | 8.5 | 75.0 | 6.4 |
| 18 | Conduct Miscellaneous Business Activities | 3.0 | 50.0 | 1.5 |
| 19 | Revisions | 1.0 | 20.0 | 0.2 |
|  | EFFECTIVE PERCENT OF PHASE IV: |  |  |  |
|  | WORK COMPLETED TO DATE |  |  | 74.5 |
|  | LESS WORK COMPLETED TO DATE LAST INVOICE |  |  | 70.8 |
|  | WORK COMPLETED THIS PAY PERIOD* |  |  | 3.7 |

NET FEE CEILING                                            $10,000.00

*WORK COMPLETED THIS PAY PERIOD               x 3.7%

-------------

NET FEE THIS PAY PERIOD                          $     370.00

ALSO SUPPLY A BRIEF NARRATIVE OF YOUR PROGRESS AS WELL

Revised 7/2/2015 071/30/2000