## VE Analysis Schedule
VE Analysis Schedule
2026-08-05 02:34 | [7 empty] | NOTE: Project Analysis Schedule Based on 12-23-16 PPRM Download
Letting | Analysis |  |  | PIN | County | Route | ROW Turn-in Date ** | Termini
| *Status | Year | Organize
2018-05-11 | YES | 2017 | 1st Quarter | 100241.02 | Knox | SR-115 | 2017-05-09 | From North of Little River to North of Maloney Road
2018-08-17 | YES | 2017 | 1st Quarter | 100241.03 | Knox | SR-115 | 2017-08-07 | From Woodson Drive to Cherokee Trail Interchange
2017-08-18 | Yes | 2017 | 1st Quarter | 114149.02 | Madison | I-40 |  | From West of SR-186(US-45 ByPass) to East of SR-5(North Highland Ave)
2018-12-07 | MAYBE | 2017 | 1st Quarter | 105764 | Scott | SR-29 PROP | 2017-06-06 | Oneida ByPass; 5-LN section North of Oneida to 5-LN Section South of Oneida (EPD)
2018-06-22 | MAYBE | 2017 | 1st Quarter | 107913 | Shelby | I-240 | 2017-06-28 | Interchange at Airways Blvd
2018-10-05 | YES | 2017 | 2nd Quarter | 101407.01 | Campbell | SR-63 | 2017-07-14 | (General Carl W. Stinger Hwy.), From Near Myers Lane (LaFollette City Limits) to Frontier Road/Woodson Lane
2018-06-22 | YES | 2017 | 2nd Quarter | 101409 | Claiborne | SR-63 | 2017-07-24 | From Campbell County Line to Hall Lane
2017-12-08 | YES | 2017 | 2nd Quarter | 105763 | Claiborne | SR-63 | 2017-01-30 | From West of Old Town Creek to SR-32 (US-25E) (EPD)
2018-08-17 | YES | 2017 | 2nd Quarter | 101407.02 | Campbell | SR-63 | 2017-07-14 | (General Carl W. Stinger Hwy.), From Frontier Road/Woodson Lane to Claiborne County Line
2018-10-05 | YES | 2017 | 2nd Quarter | 101651.03 | Blount | SR-115 | 2017-08-14 | (Relocated Alcoa Highway), From SR-162 (Pellissippi Parkway) to South Singleton Station Road
2019-10-04 | YES | 2017 | 2nd Quarter | 101651.02 | Blount | SR-115 | 2017-08-24 | (Relocated Alcoa Highway), From Proposed Interchange at Tyson Boulevard to SR-162 (Pellissippi Parkway)
2018-08-17 | MAYBE | 2017 | 2nd Quarter | 112833 | Hamilton | I-24 | 2017-05-08 | Interchanges at SR-2(Broad Street) and SR-58(Market Street) in Chattanooga
2019-10-18 | YES | 2017 | 2nd Quarter | 101411.03 | Morgan | SR-29 | 2017-08-30 | North of Ray Cross Rd/Mossy Grove Rd(Formerly Westminster Rd) to SR-62 in Wartburg
2017-12-08 | YES | 2017 | 2nd Quarter | 101651.01 | Blount | SR-115 | 2016-09-30 | (Relocated Alcoa Highway), From SR-35(Hall Road), South of Airport Road to Proposed Interchange at Tyson Boulevard
2017-12-08 | YES | 2017 | 2nd Quarter | 101454.01 | Williamson | SR-397 | 2009-12-10 | Mack Hatcher Parkway West, From South of SR-96 West of Franklin to East of SR-106 (US-431) North of Franklin
2018-12-07 | YES | 2017 | 2nd Quarter | 101589.01 | Coffee | SR-55 | 2017-04-03 | First Avenue to SR-16 (US-41A, N Jackson Street) in Tullahoma
2017-12-08 | YES | 2017 | 2nd Quarter | 115791 | Wilson | I-40 | 2015-09-14 | From East of SR-109 to East of SR-840
2019-06-21 | MAYBE | 2017 | 2nd Quarter | 107774.01 | Fentress | SR-28 | 2017-09-27 | (S. York Hwy.), Near Little Road, North of SR-62 to North Kilby Road
2018-12-07 | YES | 2017 | 3rd Quarter | 101609.02 | Shelby | SR-1 |  | Summer Avenue, From 0.1 Mile North of Sycamore View Road To 0.1 Mile North of Elmore Road
2017-12-08 | YES | 2017 | 3rd Quarter | 101609.01 | Shelby | SR-1 |  | Summer Avenue, From I-40 to 0.1 Mile North of Sycamore View Road
2017-12-08 | MAYBE | 2017 | 3rd Quarter | 101645 | Shelby | SR-57 | 2010-08-10 | Bridges over SR-23, CSXT & IC Railroad, Union Pacific Railway and Scott Street, LM 1.88 in Memphis
2019-10-04 | YES | 2017 | 4th Quarter | 100241.01 | Blount | SR-115 | 2018-02-19 | (Alcoa Highway); Pellissippi Parkway to North of Little River
| * | Yes indicates a study is anticipated. Maybe indicates the need for a study will be determined when a cost estimate is available.
| ** | Date is based on PPRM Activity Code 600. A blank space indicates the project has no PPRM Activity Code 600.