## schedule
VE Analysis Schedule
2017-05-01 | [7 empty] | NOTE: Project Analysis Schedule Based on 4-27-17 PPRM Download
2017-07-13 | [7 empty] | NOTE: Project Analysis Schedule Based on 6-29-17 PPRM Download
Letting | Analysis |  |  | PIN | County | Route | ROW Turn-in Date ** | Termini
| *Status | Year | Organize
2019-10-04 | YES | 2017 | 3rd Quarter | 101411.03 | Morgan | SR-29 | 2017-09-18 | North of Ray Cross Rd/Mossy Grove Rd(Formerly Westminster Rd) to SR-62 in Wartburg
2018-12-07 | YES | 2017 | 3rd Quarter | 107913 | Shelby | I-240 | 2017-12-13 | Interchange at Airways Blvd
2018-02-09 | YES | 2017 | 3rd Quarter | 101454.01 | Williamson | SR-397 | 2009-12-10 | Mack Hatcher Parkway West, From South of SR-96 West of Franklin to East of SR-106 (US-431) North of Franklin
2018-05-11 | YES | 2017 | 4th Quarter | 107532 | Shelby | I-40 |  | SR-177(Germantown Road) to East of Canada Road
2019-02-08 | YES | 2018 | 1st Quarter | 101651.02 | Blount | SR-115 | 2017-12-01 | (Relocated Alcoa Highway), From Proposed Interchange at Tyson Boulevard to SR-162 (Pellissippi Parkway)
2019-10-04 | YES | 2018 | 1st Quarter | 100241.01 | Blount | SR-115 | 2018-04-18 | (Alcoa Highway); Pellissippi Parkway to South of Topside Road.
2019-05-10 | YES | 2018 | 1st Quarter | 114149.01 | Madison | I-40 | 2018-05-11 | From East of SR-5(US-45) to SR-1(US-70) in Jackson
2018-12-07 | YES | 2018 | 1st Quarter | 114149.03 | Madison | I-40 |  | From West of SR-20 (US-412, Hollywood Drive) to West of SR-186 (US-45 ByPass)
2018-10-05 | YES | 2018 | 1st Quarter | 100326.01 | Gibson | SR-76 | 2017-01-20 | From West of Cades-Atwood Road to East of SR-77
2018-10-05 | YES | 2018 | 1st Quarter | 100326.02 | Carroll | SR-76 | 2017-01-20 | From East of SR-77 to West of Cutlip Lane
2019-08-16 | YES | 2018 | 1st Quarter | 100326.03 | Carroll | SR-76 | 2018-06-28 | From West of Cutlip Lane to West of Sydnor Rd/Winston Rd
2018-10-05 | YES | 2018 | 1st Quarter | 101407.01 | Campbell | SR-63 | 2017-08-28 | (General Carl W. Stiner Hwy.), From Near Myers Lane (LaFollette City Limits) to Near Frontier Road/Woodson Lane
2018-08-17 | YES | 2018 | 1st Quarter | 101407.02 | Campbell | SR-63 | 2017-08-28 | (General Carl W. Stiner Hwy.), From Near Frontier Road/Woodson Lane to Near Claiborne County Line
2018-12-07 | YES | 2018 | 1st Quarter | 105763 | Claiborne | SR-63 | 2017-08-01 | From West of Old Town Creek to SR-32 (US-25E) (EPD)
2019-12-06 | YES | 2018 | 1st Quarter | 101409 | Claiborne | SR-63 | 2017-10-18 | From Campbell County Line to Hall Lane
2017-12-08 | YES | 2018 | 2nd Quarter | 101609.01 | Shelby | SR-1 |  | Summer Avenue, From I-40 to 0.1 Mile North of Sycamore View Road
2018-12-07 | YES | 2018 | 2nd Quarter | 101609.02 | Shelby | SR-1 |  | Summer Avenue, From 0.1 Mile North of Sycamore View Road To 0.1 Mile North of Elmore Road
2019-03-22 | YES | 2018 | 2nd Quarter | 101589.01 | Coffee | SR-55 | 2017-05-10 | First Avenue to SR-16 (US-41A, N Jackson Street) in Tullahoma
2018-12-07 | YES | 2018 | 3rd Quarter | 101419.04 | Hamblen | SR-34 | 2017-07-31 | (E. Andrew Johnson Hwy.), From Near Morris Blvd to West of Old Stagecoach Road in Russellville (***)
2018-12-07 | YES | 2018 | 3rd Quarter | 101419.02 | Hamblen | SR-34 | 2017-06-30 | From West of Old Stagecoach Road in Russellville to Steadman Road (EPD)
2019-06-21 | YES | 2018 | 3rd Quarter | 101419.03 | Hamblen | SR-34 | 2016-09-30 | From SR-32 in Morristown to Near East Morris Boulevard
2019-05-10 | YES | 2018 | 3rd Quarter | 100260.05 | Cumberland | SR-28 | 2012-01-20 | South of Lowe Road to SR-62 in Fentress County
2019-06-21 | YES | 2018 | 3rd Quarter | 100260.01 | Cumberland | SR-28 | 2013-09-12 | North of I-40 to Near Legion Road
| * | Yes indicates a study is anticipated. Maybe indicates the need for a study will be determined when a cost estimate is available.
| ** | Date is based on PPRM Activity Code 600. A blank space indicates the project has no PPRM Activity Code 600.