## Sheet1
VE Analysis Schedule
2016-10-13 13:56 | [7 empty] | NOTE: Project Analysis Schedule Based on 9-30-16 PPRM Download
Letting | Analysis |  |  | PIN | County | Route | ROW Turn-in Date ** | Termini
| *Status | Year | Organize
2017-12-08 | Yes | 2016 | 4th Quarter | 101651.01 | Blount | SR-115 | 2016-09-30 | (Relocated Alcoa Highway), From SR-35(Hall Road), South of Airport Road to Proposed Interchange at Tyson Boulevard
2017-12-08 | Yes | 2017 | 1st Quarter | 101454.01 | Williamson | SR-397 | 2009-12-10 | Mack Hatcher Parkway West, From South of SR-96 West of Franklin to East of SR-106 (US-431) North of Franklin
2017-08-18 | Yes | 2017 | 1st Quarter | 114149.02 | Madison | I-40 |  | From West of SR-186(US-45 ByPass) to East of SR-5(North Highland Ave)
2018-12-07 | Yes | 2017 | 1st Quarter | 114149.03 | Madison | I-40 |  | From West of SR-20(Hollywood Drive) to West of SR-186(US-45 ByPass)
2017-12-08 | Yes | 2017 | 1st Quarter | 101609.01 | Shelby | SR-1 |  | Summer Avenue, From I-40 to 0.1 Mile North of Sycamore View Road
2017-12-08 | Yes | 2017 | 1st Quarter | 105763 | Claiborne | SR-63 | 2016-11-14 | From West of Old Town Creek to SR-32 (US-25E) (EPD)
2017-12-08 | Maybe | 2017 | 1st Quarter | 115791 | Wilson | I-40 | 2015-09-14 | From East of SR-109 to East of SR-840
2018-06-22 | Yes | 2017 | 2nd Quarter | 101409 | Claiborne | SR-63 | 2017-06-15 | From Campbell County Line to Hall Lane
2017-12-08 | Maybe | 2017 | 2nd Quarter | 101645 | Shelby | SR-57 | 2010-08-10 | Bridges over SR-23, CSXT & IC Railroad, Union Pacific Railway and Scott Street, LM 1.88 in Memphis
2018-02-09 | Maybe | 2017 | 2nd Quarter | 107913 | Shelby | I-240 | 2017-03-09 | Interchange at Airways Blvd
2018-05-11 | Yes | 2017 | 3rd Quarter | 100241.02 | Knox | SR-115 | 2017-02-20 | From North of Little River to North of Maloney Road
2018-06-22 | Yes | 2017 | 3rd Quarter | 100260.01 | Cumberland | SR-28 | 2013-09-12 | North of I-40 to Near Legion Road
2018-05-11 | Yes | 2017 | 3rd Quarter | 107532 | Shelby | I-40 |  | SR-177(Germantown Road) to East of Canada Road
2018-08-17 | Yes | 2017 | 3rd Quarter | 100241.03 | Knox | SR-115 | 2017-05-08 | From Woodson Drive to Cherokee Trail Interchange
2018-06-22 | Yes | 2017 | 3rd Quarter | 101589.01 | Coffee | SR-55 | 2017-03-29 | First Avenue to SR-16 (US-41A, N Jackson Street) in Tullahoma
2018-08-17 | Maybe | 2017 | 3rd Quarter | 112833 | Hamilton | I-24 | 2017-07-31 | Interchanges at SR-2(Broad Street) and SR-58(Market Street) in Chattanooga
2018-08-17 | Yes | 2017 | 4th Quarter | 100260.05 | Cumberland | SR-28 | 2012-01-20 | South of Lowe Road to SR-62 in Fentress County
2018-08-17 | Yes | 2017 | 4th Quarter | 101407.02 | Campbell | SR-63 | 2017-06-15 | From Frontier Road/Woodson Lane to Claiborne County Line
2018-08-17 | Yes | 2017 | 4th Quarter | 101419.03 | Hamblen | SR-34 | 2016-09-15 | From SR-32 in Morristown to Near East Morris Boulevard
2018-08-17 | Yes | 2017 | 4th Quarter | 101419.04 | Hamblen | SR-34 | 2016-10-26 | From Near Morris Blvd to West of Old Stagecoach Road in Russellville (EPD)
| * | Yes indicates a study is anticipated. Maybe indicates the need for a study will be determined when a cost estimate is available.
| ** | Date is based on PPRM Activity Code 600. A blank space indicates the project has no PPRM Activity Code 600.